## Milestone
RELEX SYSTEM TASK TRACKING SHEET
Releases & Milestones

Release #	Purposed Date	Milestones
v0.1	30th of April	1. Driver Mobile App can scan parcels to add them to Relex system; / 2. Store Mobile App can show parcels address on the map. User can scan the parcel to update its status;
v0.2	30th of June	1. Store Mobile App can communicate with Yun Express API to obtain parcel details / 2. Admin Website can manage the parcels / 3. Driver Mobile App has optimazation route recommandation
v0.3	15th of July	Better user experiences and route plan than above
v1.0 Beta	14 of Sep	Working version for muti drivers with more necessary fucntions

## Mobile_Driver
RELEX SYSTEM TASK TRACKING SHEET
Driver Mobile APP

#	PRIORITY	TASK NAME	REQUIREMENT	COMMENTS	POINTS	ASSIGN TO	COMPLETED
1	High	User Login	User login handling with web api		3	Xin
2	High	Create a job	Create a new job by scan one or more parcel bar code	1. User can remove a parcel from the job / 2. after all parcels added to the job, then user clicks confirm button, the job created in DB with the linked user and parcels etc	3
3	High	Show estimated total travel distance of the job	By using Google Map API, the mobile app can calculate and show the estimated total travel distance of the job.		3
4	High	Show estimated total travel time of the job	By using Google Map API, the mobile app can calculate and show the estimated total travel time of the job.	Route plan starts from the inventory and ends at the inventory	3
5	High	Show all parcel addresses as PIN in the mobile app buil-in map	1. Show all parcel addresses as PIN in the mobile app buil-in map / 2. If more than one parcel associated to the same address, there should be a number indicating around the PIN		3
6	Mid	By comparing to the inventory coordinates, highlights the nearest parcel address PIN	By comparing to the inventory coordinates, highlights the nearest parcel address PIN	Make that PIN diferent color or bigger	2
7	High	User can scan a parcel and mark it as delivered	When a parcel accepted by end customer, user can scan the parcel and mark it delivered. A web api will be called to record this in DB	After DB updated, the web API return a message to front end then this action is done	3
8	High	User can scan a parcel and mark it as failed to delivered with a reason	When the driver cannot deliver the parcel with a list of pre defined reason. The driver can mark it as failed to delivered	After DB updated, the web API return a message to front end then this action is done	3

## Mobile_Store
RELEX SYSTEM TASK TRACKING SHEET
Store Admin Mobile APP

#	PRIORITY	TASK NAME	REQUIREMENT	COMMENTS	POINTS	ASSIGN TO	COMPLETED
1	High	User Login	User login handling with web api	API : /login	3	Xin
2		Scan Parcel	Scan parcel to Relex system	API : /getparceldetails / API : /createparcel / API : /statusupdate	5
3		Scan Parcel Success	Pop up tray id for parcel to go		3
4		Scan Parcel Failed	Pop up warning and let user decide what to do		3
5
6
7
8

## Web_APIs
RELEX SYSTEM TASK TRACKING SHEET
WEB APIs

#	PRIORITY	TASK NAME	REQUIREMENT	COMMENTS	POINTS	ASSIGN TO	COMPLETED
1	High	User Login	1. Front end calls this API with user name and password / 2. Password is encrypted in DB / 3. Return success or failed message back to front end / 4. Update user table if success	[Endpoint] / login / [payload] / username: string / password: string / [retrun] / success: 'success' / failed: 'failed'	3	Di( the whole Authorization backend including (signin, signout, refresh token)will be provided by AWS congnito user pools service and API gateway)
2	High	Static IP for Web APIs	Assign static IP to the web API so mobile app can talk to it anywhere		3	Di (swagger api doc)
3	Low	SSL cert for Web APIs	Assign SSL cert so web API is https		3
4	High	Create a job	Front end calls with API to create a job with linked parcels and user	[Endpoint] / createjob / [payload] / username: string / parcelids: array[string] / [retrun] / success: jobid / failed: 'failed'	2
5	High	API to change parcel statue	Every time the parcel status got changed, the DB will updated. We need our APIs to handle this	[Endpoint] / statusupdate / [payload] / username: string / jobid: string / parcelid: string / newstatus: string / reason: string / [retrun] / success: 'success' / failed: 'failed'	5
6	High	Fake Yun API	An Fake API to return parcel details based on barcode	[EndPoint] / getparceldetails / [Payload] / barcode: string / [return] / parceldetails : json obj
7	High	Create a parcel	A parcel will be created in the DB after scanned by the sote admin	[EndPoint] / createparcel / [Payload] / parcel details with parcel barcode / [return] / tray id

## DB
RELEX SYSTEM TASK TRACKING SHEET
DB

#	PRIORITY	TASK NAME	REQUIREMENT	COMMENTS	POINTS	ASSIGN TO	COMPLETED
1	HIGH	Create DB with some essential sample data	1. Create DB based on requirement v0.1 / 2. Create a sample user	1. Password should be displayed in encrypted / 2. Allow some of table fields nullable because we do not have these information at this stage	6
2	HIGH	Fake Parcel Table / Hardcoded json	Create a fake parcel table with 20 entries of sample data	For Fake Yun Express API	2